ENGINEERING PROJECT CHARTER

Document ID: PROJ-CHARTER-AETH100-REV-A

Project Title: Aether100 Pro Edge AI Workstation Hardware Platform

Revision: Rev A (Baseline Production Release)

Effective Date: July 31, 2026

Classification: Standard Operating Specification / Technical Data Package

REVISION HISTORY

| Rev | Description of Change | Prepared By | Approved By | Release Date |
| --- | --- | --- | --- | --- |
| A | Initial BaselineTechnicalCharterRelease | SystemsEngineeringGroup | ExecutiveReview Board | 2026-07-31 |

1. PROJECT OVERVIEW & TITLE

● Project Name: Aether100 Pro Edge AI Workstation Hardware Platform

● Project Code: AETH100-PRO

● Project Lead: Lead Hardware Systems Architect

● Sponsoring Entity: Aether Technologies Systems Engineering Group

1.1 Executive Summary

The Aether100 Pro project encompasses the complete mechanical, thermal, electrical, and firmware design, validation, and turnkey manufacturing release of a workstation-grade local edge AI appliance. The unit is engineered to execute 70-billion-parameter neural networks locally with zero cloud dependencies. It features a custom TSMC 3nm System-on-Chip (ACE-1), 256 GB LPDDR5X-8533 memory over a 2,048-bit bus, dual PCIe Gen5 x4 enterprise NVMe drives, a 12-layer MEGTRON 7 High-Density Interconnect (HDI) PCB, and a two-phase copper vapor chamber thermal subsystem. The unit maintains an ultra-quiet acoustic profile of

at 1.0 m within a continuous thermal dissipation envelope.

2. PROJECT OBJECTIVES & SUCCESS CRITERIA

2.1 Quantitative Technical Objectives

1. Thermal Dissipation: Continuous dissipation of active compute load while

maintaining silicon die junction temperature in a ambient

environment.

2. Acoustic Emissions: Sound pressure level emissions measured at

1.0 m distance under 100% sustained tensor execution.

3. Data Ingestion Throughput: Sustained sequential read bandwidth across

a dual PCIe Gen5 x4 enterprise NVMe array utilizing 100% Flash Translation Layer (FTL)

over-provisioning.

4. Reliability & Lifespan: Mean Time Between Failures at continuous operation; BGA solder joint low-cycle fatigue life .

5. Manufacturing First-Pass Yield: SMT line first-pass yield with zero

structural or electrical major non-conformances.

3. PROJECT SCOPE

3.1 In-Scope

● Mechanical & Thermal Design: 3D CAD modeling (STEP AP242 / Parasolid), 6061-T6

aluminum CNC unibody enclosure, sealed copper vapor chamber plate (

), 140mm fluid dynamic bearing (FDB) fan integration, finite

element analysis (FEA), and computational fluid dynamics (CFD) thermal verification.

● Electrical & Electronics: 12-layer MEGTRON 7 HDI PCB schematic design, 2,048-bit

LPDDR5X-8533 memory routing, power delivery network (PDN) transient optimization (

), multi-phase PMIC integration, and 0201 MLCC substrate cavity

decoupling.

● Firmware & Low-Level Driver Development: U-Boot SPL bootloader initialization,

io_uring zero-interrupt storage polling daemon, aether-thermal 100 Hz PMU micro-sleep

governor, and early-boot hardware diagnostic probe (aether-hw-probe).

● Manufacturing TDP Release: Full ASME Y14.5-2018 2D drawing package, multi-level

BOM, assembly work instructions (SOP), First Article Inspection (AS9102 FAI) plan, and IPC

Class 3 fabrication specifications.

3.2 Out-of-Scope

● Public cloud SaaS infrastructure development or multi-tenant hosting remote software

services.

● Semiconductor front-end wafer mask tooling or fab line operations (ACE-1 SoC purchased

as finished ASIC).

● High-touch corporate sales distribution setup (platform released under open-hardware

repository and direct-to-order manufacturing).

4. MAJOR DELIVERABLES & MILESTONE SCHEDULE

| Phase | Milestone Gate | DeliverableDescription | Target Completion |
| --- | --- | --- | --- |
| Phase 1 | Gate 1 (M1) | System Architecture & Schematic Freeze Release | Month 2 |
| Phase 2 | Gate 2 (M2) | EVT Hardware Prototypes & SI/PI Validation Sign-Off | Month 4 |
| Phase 3 | Gate 3 (M3) | DVT Mechanical, Thermal, & Environmental Validation | Month 7 |
| Phase 4 | Gate 4 (M4) | Regulatory Certification (FCC Part 15 Class B, CE, UL 94V-0) | Month 10 |
| Phase 5 | Gate 5 (M5) | PVT Mass Production Ramp (1,200 Units Pilot Batch) | Month 12 |

5. PROJECT CONSTRAINTS & ASSUMPTIONS

5.1 Constraints

● Unit BOM Cost Cap: Maximum target manufacturing BOM cost

at 1,000-unit production volumes.

● Enclosure Form Factor Envelope: Maximum outer dimensions

.

● Input Power Interface: Single input voltage interface rated for

max continuous current via external GaN power adapter.

5.2 Assumptions

● Tier-1 EMS partners maintain IPC-A-610 Class 3 and IPC-A-600 Class 3 certified

manufacturing lines.

● Panasonic MEGTRON 7 (R-5785N) dielectric substrate supply chains maintain lead times

.

● Monolithic silicon ASIC revision (ACE-1) meets pinout and power specifications without

requiring silicon re-spins.

6. KEY STAKEHOLDERS & RACI AUTHORITY MATRIX

6.1 RACI Definitions

● R - Responsible: The role that completes the activity.

● A - Accountable: The role with final approval authority.

● C - Consulted: Subject matter expert consulted during engineering design.

● I - Informed: Role notified of decisions and status progress.

6.2 RACI Matrix

| Activity / Work Package | LeadSystemsArchitect | Lead MechEngineer | Lead ElecEngineer | QA / Regulatory Lead | EMSProgramManager |
| --- | --- | --- | --- | --- | --- |
| Architectu re Definition | A / R | C | C | C | I |
| CAD & Thermal Design | A | R | C | I | C |
| PCB Schematic & Layout | A | C | R | I | C |
| SI / PI Analysis | A | I | R | I | I |

| Drawing & BOM Release | A | R | R | C | C |
| --- | --- | --- | --- | --- | --- |
| Regulatory Complianc e | A | I | C | R | I |
| PVT Ramp & FAI Audit | A | C | C | R | R |

7. HIGH-LEVEL RISK SUMMARY

1. LPDDR5X Signal Degradation: Crosstalk across 2,048-bit bus at 8533 MT/s causing bit

errors (Mitigation: MEGTRON 7 substrate + stripline routing).

2. Core Rail Transient Voltage Droop: load step causing rail collapse beyond

window (Mitigation: 120x MLCC BGA substrate cavity array).

3. Thermal Throttling in Silent Mode: Sustained load exceeding

ceiling at 500 RPM fan speed (Mitigation: 100 Hz PMU micro-sleep

governor).

4. Substrate Supply Chain Delays: Lead time spikes on MEGTRON 7 laminate impacting

schedule (Mitigation: Pre-qualify Isola Tachyon 100G).

8. BUDGET & FINANCIAL ALLOCATION

| Budget Category | Allocation ($ USD) | Percentage (%) | PrimaryExpenditure Scope |
| --- | --- | --- | --- |
| Silicon & Component Tooling | 34.3% | TSMC 3nm NRE allocations, ASIC packaging dies |  |
| HardwareEngineeringTooling | 18.6% | CNC unibody molds, vapor chamber tooling dies |  |
| Systems & Firmware R&D | 22.8% | Kernel isolation, SVE2 assembly, CVE |  |

| engine |
| --- |
| ComplianceTesting | 4.3% | FCC Part 15 Class B, CE, UL 94V-0 chamber certification |
| NPI Pilot Production & Scrap | 12.9% | 1,200-unit pilot run, SMT stencil line setup |
| ManagementContingency | 7. 1% | Supply chain buffer, component price hedging |
| TOTAL PROJECTALLOCATION | 100.0% | Full Program NPIRelease |

9. APPROVAL SIGNATURES BLOCK

APPROVED BY:

Lead Hardware Systems Architect

Date: July 31, 2026

Lead Mechanical & Thermal Engineer

Date: July 31, 2026

Lead Electrical & Firmware Engineer

Date: July 31, 2026

Director of Quality Assurance & Operations

Date: July 31, 2026